## WBS
지능형 미아방지 시스템_WBS | [27 empty] | FE&BE 데드라인
| 시작일 |  |  | 2020-05-15 |  |  |  | 작업일정
| 종료일 |  |  | 2020-10-31 결과보고서 제출 마감
[5 empty] | 월별 |  | M | 5월 | [16 empty] | 6월 | [29 empty] | 7월 | [30 empty] | 8월 | [30 empty] | 9월 | [29 empty] | 10월
[5 empty] | 주차 |  | W | 1w | [6 empty] | 2w | [6 empty] | 3w | [6 empty] | 4w | [6 empty] | 5W | [6 empty] | 6W | [6 empty] | 7W | [6 empty] | 8W | [6 empty] | 9W | [6 empty] | 10W | [6 empty] | 11W | [6 empty] | 12W | [6 empty] | 13W | [6 empty] | 14W | [6 empty] | 15W | [6 empty] | 16W | [6 empty] | 17W | [6 empty] | 18W | [6 empty] | 19W | [6 empty] | 20W | [6 empty] | 21W | [6 empty] | 22W | [6 empty] | 23W | [6 empty] | 24W | [6 empty] | 25W
[5 empty] | 요일 |  | D1 | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat
[5 empty] | 일별 |  | D2 | 2020-05-15 | 2020-05-16 | 2020-05-17 | 2020-05-18 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-23 | 2020-05-24 | 2020-05-25 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-05-30 | 2020-05-31 | 2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-06 | 2020-06-07 | 2020-06-08 | 2020-06-09 | 2020-06-10 | 2020-06-11 | 2020-06-12 | 2020-06-13 | 2020-06-14 | 2020-06-15 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19 | 2020-06-20 | 2020-06-21 | 2020-06-22 | 2020-06-23 | 2020-06-24 | 2020-06-25 | 2020-06-26 | 2020-06-27 | 2020-06-28 | 2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-04 | 2020-07-05 | 2020-07-06 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10 | 2020-07-11 | 2020-07-12 | 2020-07-13 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17 | 2020-07-18 | 2020-07-19 | 2020-07-20 | 2020-07-21 | 2020-07-22 | 2020-07-23 | 2020-07-24 | 2020-07-25 | 2020-07-26 | 2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02 | 2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31
| 담당 | WBS | 구분 | 항목 | 상태 | 진척도
|  | 1 | 프로세스 확립 |  | 작업 대기 | 0%
|  | 1.1 | 프로세스 기초 작업 |  | 작업 대기 | 0%
|  |  | 1.1.1 | 미아방지 대책 방법 자료 조사 | 작업 대기 | 0% | bar: D2
|  |  | 1.1.2 | 조사한 자료 정리 | 작업 대기 | 0% | bar: D2 to 2020-05-15
|  |  | 1.1.3 | 시스템 설계 | 작업 대기 | 0% | bar: 2020-05-15 to 2020-05-18
|  | 1.2 | 프로세스 구성 |  | 작업 대기 | 0%
| 최한수 |  | 1.2.1 | 기능명세서 작성(요구사항 도출) | 작업 대기 | 0% | bar: 2020-05-15 to 2020-05-16
| 이민규, 박진수 |  | 1.2.2 | 화면설계서 작성 | 작업 대기 | 0% | bar: 2020-05-15 to 2020-05-16
| 이민규, 박진수 |  | 1.2.3 | 화면별 기능명세서 작성 | 작업 대기 | 0% | bar: 2020-05-17
| 최한수, 김민규 |  | 1.2.4 | 테이블 명세서 작성 | 작업 대기 | 0% | bar: 2020-05-15 to 2020-05-17
|  | 2 | 산출물 |  | 작업 대기 | 0%
|  | 2.1 | 산출물 |  | 작업 대기 | 0%
| 최한수 |  | 2.1.1 | 프로세스 설계도 작업 | 작업 대기 | 0% | bar: 2020-05-15 to 2020-05-18; 2020-05-30
| 최한수 |  | 2.1.2 | 프로세스 설계도 일반화 작업 (어플리케이션과 연계 필요) | 작업 대기 | 0% | bar: 2020-05-31 to 2020-06-01
|  | 2.2 | 검토 |  | 작업 대기 | 0%
| 최한수 |  | 중간 검토 | 개발 & 자료 중간 검토 | 작업 대기 | 0% | bar: 2020-06-02 to 2020-06-04
|  | 3 | 개발/구현 |  | 작업 대기 | 0%
| 박진수, 이민규 | 3.1 | FE |  | 작업 대기 | 0%
| 박진수 |  | 3.1.1 | 부모, 아이 선택 | 작업 대기 | 0% | bar: 2020-05-18
| 박진수 |  | 3.1.2 | (아이) 비밀번호 입력 | 작업 대기 | 0% | bar: 2020-05-19
| 박진수 |  | 3.1.3 | (아이) 고유키 생성 | 작업 대기 | 0% | bar: 2020-05-20 to 2020-05-21
| 박진수 |  | 3.1.4 | (아이) 고유키 + 비밀번호 서버 통신 | 작업 대기 | 0% | bar: 2020-05-21 to 2020-05-23
| 박진수 |  | 3.1.5 | (아이) 지속적인 사용자 확인 | 작업 대기 | 0% | bar: 2020-05-24 to 2020-05-25
| 박진수 |  | 3.1.6 | (아이) SOS 버튼 | 작업 대기 | 0% | bar: 2020-05-26 to 2020-05-27
| 박진수 |  | 3.1.7 | (부모) 로그인 | 작업 대기 | 0% | bar: 2020-05-28
| 박진수 |  | 3.1.8 | (부모) 회원가입 | 작업 대기 | 0% | bar: 2020-05-29
| 박진수 |  | 3.1.9 | (부모) 아이디 찾기 | 작업 대기 | 0% | bar: 2020-05-30 to 2020-05-31
| 박진수 |  | 3.1.10 | (부모) 비밀번호 재설정 | 작업 대기 | 0% | bar: 2020-05-31 to 2020-06-01
| 이민규 |  | 3.1.11 | (부모) 지문인식 | 작업 대기 | 0% | bar: 2020-05-31 to 2020-06-01
| 이민규 |  | 3.1.12 | (부모) 아이리스트(메인화면) | 작업 대기 | 0% | bar: 2020-05-18 to 2020-05-19
| 이민규 |  | 3.1.13 | (부모) 아이 추가 | 작업 대기 | 0% | bar: 2020-05-20 to 2020-05-21
| 이민규 |  | 3.1.14 | (부모) 아이 정보 확인 | 작업 대기 | 0% | bar: 2020-05-21
| 이민규 |  | 3.1.15 | (부모) 아이 위치확인 | 작업 대기 | 0% | bar: 2020-05-22 to 2020-05-23
| 이민규 |  | 3.1.16 | (부모) 아이 정보 수정 및 초기 위치값 설정 | 작업 대기 | 0% | bar: 2020-05-24
| 이민규 |  | 3.1.17 | (부모) 아이 SOS 팝업 | 작업 대기 | 0% | bar: 2020-05-25 to 2020-05-26
| 이민규 |  | 3.1.18 | (부모) 아이 경로 위험상황 팝업 | 작업 대기 | 0% | bar: 2020-05-26 to 2020-05-27
| 이민규 |  | 3.1.19 | (부모) 실종 아이 리스트 | 작업 대기 | 0% | bar: 2020-05-27 to 2020-05-28
| 이민규 |  | 3.1.20 | (부모) 실종 아이 정보 확인 | 작업 대기 | 0% | bar: 2020-05-28 to 2020-05-29
| 이민규 |  | 3.1.21 | (부모) 실종 아이 위치확인 | 작업 대기 | 0% | bar: 2020-05-29 to 2020-05-30
| 최한수, 김민규 | 3.2 | BE |  | 작업 대기 | 0%
|  |  | 3.2.1 | 테이블 생성 | 작업 대기 | 0%
|  |  | 3.2.2 | 관계 구현 | 작업 대기 | 0%
|  |  | 3.2.3 | DB 제약조건 위배 제거 | 작업 대기 | 0%
| 김민규 |  | 3.2.4 | 회원가입 | 작업 대기 | 0% | bar: 2020-05-18
| 김민규 |  | 3.2.5 | 로그인 | 작업 대기 | 0% | bar: 2020-05-18
| 김민규 |  | 3.2.6 | 아이디찾기 | 작업 대기 | 0% | bar: 2020-05-19
| 김민규 |  | 3.2.7 | 비밀번호 재설정 | 작업 대기 | 0% | bar: 2020-05-19
| 김민규 |  | 3.2.8 | 아이등록 | 작업 대기 | 0% | bar: 2020-05-20 to 2020-05-22
| 김민규 |  | 3.2.9 | 아이 정보수정 | 작업 대기 | 0% | bar: 2020-05-22 to 2020-05-25
| 김민규 |  | 3.2.10 | 아이 초기 위치값 설정 | 작업 대기 | 0% | bar: 2020-05-26 to 2020-05-29
| 김민규 |  | 3.2.11 | 아이 SOS 상황 등록 | 작업 대기 | 0% | bar: 2020-05-30
| 김민규 |  | 3.2.12 | 아이 위험상황 등록(경로이탈) | 작업 대기 | 0% | bar: 2020-05-31
| 김민규 |  | 3.2.13 | 아이 실종 여부 등록 | 작업 대기 | 0% | bar: 2020-06-01
| 최한수 |  | 3.2.14 | 아이 목록조회 | 작업 대기 | 0% | bar: 2020-05-18 to 2020-05-19
| 최한수 |  | 3.2.15 | 아이 정보 조회 | 작업 대기 | 0% | bar: 2020-05-20 to 2020-05-21
| 최한수 |  | 3.2.16 | 아이 실시간 위치 등록 | 작업 대기 | 0% | bar: 2020-05-22
| 최한수 |  | 3.2.17 | 아이 위치 조회 | 작업 대기 | 0% | bar: 2020-05-23 to 2020-05-24
| 최한수 |  | 3.2.18 | 실종아이 목록조회 | 작업 대기 | 0% | bar: 2020-05-25 to 2020-05-26
| 최한수 |  | 3.2.19 | 실종아이 정보조회 | 작업 대기 | 0% | bar: 2020-05-27
| 최한수 |  | 3.2.20 | 실종아이 위치조회 | 작업 대기 | 0% | bar: 2020-05-28 to 2020-05-29
|  | 3.3 | 인공지능 |  | 작업 대기 | 0%
|  |  | 3.3.1 | 위치정보와 지도 매핑 | 작업 대기 | 0%
|  |  | 3.3.2 | 누적된 위치정보 분석 | 작업 대기 | 0%
|  |  | 3.3.3 | 시간대별 경로 형성 | 작업 대기 | 0%
|  |  | 3.3.4 | 실시간 위치정보 확인 | 작업 대기 | 0%
|  |  | 3.3.5 | 경로 이탈 후 확인 조건 설정 | 작업 대기 | 0%
|  |  | 3.3.6 | 위험상황 등록 | 작업 대기 | 0%
|  |  | 3.3.7 | 실종아이 목록 조회 필터링(거리) | 작업 대기 | 0%